North Olympic Peninsula Skills Center

3-Year Plan – Goals

Framework: 8th Year: Streamline/refine program and evaluate – expand summer staffing and offerings, 9th Year: Continue to refine program and evaluate, 10th Year: Continue to refine program and evaluate – potential school-year staffing expansion

Program Name: Natural Resources								Date Submitted: May 2015

| Program Area | 2015-2016 | 2016-2017 | 2017-2018 |
| --- | --- | --- | --- |
| Curriculum / Instructional Materials | NR Options lessons digital and on class website; Program re-approval | Program re-approval; curriculum review/in-house audit by advisors or school personnel; | Explore other curriculum ideas for NR Options |
| Equipment / Facility | Size 10 boots; emergency cell and jetpack (All covered by already-confirmed grant funding) | Monitor and make purchases if necessary (Covered by already-confirmed grant funding) | Monitor and make purchases if necessary |
| Student Recruitment / Retention | 18 FTE in school year, 7 FTE in summer; Retain 75% in classes; Plan for NR Options in Crescent | 20 FTE in school year, 7 FTE in summer; Retain 80% in classes; Start NR Options in Crescent | 24 FTE in school year, 7 in summer; Retain 85% in classes; Start NR Options in Cape Flattery |
| Student Leadership (Service Learning / Internships) | 16 NR2 Interns; Find stipends + scholarships | Continue Internships, Explore more scholarship options | Continue Internships, Explore more internship options |
| Staff (Hiring / Professional Development) | Keep 1.0 teacher; 2-3 summer teachers (Options in-person, Options remote, and NR Elwha) | Keep 1.0 teacher; Again hire all three NR teachers for summer | Keep 1.0 teacher; possible 0.5 West End teacher; Again hire all three summer teachers |
| Safety / Risk Management | Revise Risk Management Plan and enrollment forms; Document all accidents/near misses | Wilderness First Responder recert training for PA teacher; Document all accidents/near misses | Create student-friendly Risk Management Plan; Document all accidents/near misses |
| Other: | Enroll students for credit through CWU and Pen. Col. | Other college credit possibilities explored | Other college credit options confirmed; |

Advisory Committee Chair Approval: __________________________   	Teacher Approval:

North Olympic Peninsula Skills Center

3-Year Plan – 2015-2016 Work Plan

Program Name: Natural Resources								Date Submitted: May 2015

| Program Area | Indicator of Success | Outcomes | Individual(s) Responsible | Timeline | End of Year Review: |
| --- | --- | --- | --- | --- | --- |
| Curriculum / Instructional Materials | 1. Lessons digital and on class website; 2. Program is approved by OSPI | 1. Students access lessons online 2. State confirms approval | 1. Dan/student intern 2. Dan/Peggy | 1. 6/16 2. 9/2015 | 1. 2. |
| Equipment / Facility | 1. Get size 10 boots 2. Cell and Jetpack refreshed | 1. Students use new boots, 2. Use emergency cell and jetpack | 1. Dan 2. Dan | 1. 12/15 2. 12/15 | 1. 2. |
| Student Recruitment / Retention | 1. 18.0 FTE in school year, 7 in summer 2. Retain 75% of students; 3. Plan for NR Options in Crescent | 1. Enrollment meets 18.0 + 7 FTE 2. 75% of students earn credit 3. Implementation plan complete | 1. Dan 2. Dan 3. Dan | 1. 8/16 2. 6/16 3. 6/16 | 1. 2. |
| Student Leadership (Service Learning / Internships) | 1. At least 16 NR 2 Interns; 2. At least 1 new student stipend | 1. At least 12 complete NR 2 2. 1 student gets new funding | 1. Dan 2. Dan 3. Dan | 1. 6/16 2. 6/16 3. 6/16 | 1. 2. 3. |
| Staff (Hiring / Professional Development) | 1. Keep 1.0 NR Teacher; 2. 1-2 NR Options and 1 NR Science teacher for summer school | 1. NR teacher full-time all year 2. 2-3 NR teachers hired for summer | 1. Dan/Peggy 2. Dan/Peggy | 1. 6/16 2. 5/16 | 1. 2. |
| Safety / Risk Management | 1. Revise risk mgmt manual + forms; 2. Document all incidents/near misses | 1. New manual and forms are used. 2. Incident forms posted in ‘Class Resources’ on NR1 website | 1. Dan 2. Dan | 1. 2/16 2. 6/16 | 1. 2. |
| Other: | 1. Enroll students for college credit through CWU and Pen. Col. | 1. At least one student earns college credit with each college | 1. Dan | 1. 6/16 | 1. |

Advisory Committee Chair Approval: __________________________   	Teacher Approval:

North Olympic Peninsula Skills Center

3-Year Plan – 2015-2016 Budget

Program Name: Natural Resources								Date Submitted: May 2015

| Program Area | Needs | Projected Cost | Proposed Funding Source |
| --- | --- | --- | --- |
| Curriculum / Instructional Materials | Streamkeepers Bug Collecting | $500 | Covered by outside funding this year |
| Equipment / Facility | Boots, Jetpack Transportation for West End Transportation for Port Angeles | $100 $600 $672 $336 | Sea Grant or other Sea Grant or other Sea Grant or other Sea Grant or other |
| Student Recruitment / Retention | Community partners recruit students for classes and help retain enrolled students | None | Community Partners |
| Student Leadership (Service Learning / Internships) | Stipends to replace now-gone student AmeriCorps awards | $3,000 for West Peninsula $3,000 for North Peninsula | NPC MRC funding hopeful Sea Grant funding secured |
| Staff (Hiring / Professional Development) | 1.0 school year and 3 summer Nat. Res. teachers | Approx. $70,000 for school year (inc. benefits) plus ~$9,000 for all 3 summer teachers [Add $5,000 in revenue] [Possibly Add $5,000 in revenue] | State funding from FTE (see budget documents in Advisory minutes) Confirmed Sea Grant Application Pending MRC Grant 2015-16 |
| Safety / Risk Management | Emergency cell phone minutes, | $100 | Sea Grant or other |
| Other: | Scholarships for students to earn 2 credits per semester for ‘Intro to Civic Engagement’ through CWU | $110 per student per semester | Feiro covers this for their student interns; Tribes might cover for Tribal students; what about non-Native and non-Feiro students?? |

Advisory Committee Chair Approval: __________________________   	Teacher Approval:

North Olympic Peninsula Skills Center

2014-2015 Work Plan Report

Program Name: Natural Resources								Date Submitted: May 2015

| Program Area | Indicator of Success | Outcomes | Individual(s) Responsible | Timeline | End of Year Review: |
| --- | --- | --- | --- | --- | --- |
| Curriculum / Instructional Materials | 1. Cultural lessons digital and on class website; 2. QUEST Skills review + add cultural QUEST skills | 1. Students access cultural lessons 2. CNR1 students use new manual and are assessed on cultural skills | 1. Dan/Jamie/ student intern 2. Dan/Jamie | 1. 6/15 2. 10/14 | 1. Not completed – Jamie transferred out 2. Cultural skills added, not assessed |
| Equipment / Facility | 1. Get size 10 boots 2. Field emergency cell retained 3. Printer in 206 remains functional 4. Grant identified for new bus/van | 1. Students use new boots, 2. Teachers use emergency cell 3. Student work is printed 4. Grant application submitted | 1. Dan 2. Dan 3. Dan 4. Jamie/Peggy | 1. 12/14 2. 12/14 3. 12/14 4. 1/15 | 1. Not purchased 2. Yes purchased 3. Printer broken 4. Not submitted |
| Student Recruitment / Retention | 1. 17.0 FTE in school year, 7 in summer - total 2. Retain 70% of CNR 1 students; | 1. Enrollment meets 17.0 + 7 FTE 2. 70% complete portfolios | 1. All/Dan/Peggy 2. Dan/Jamie | 1. 8/15 2. 6/15 | 1. Avg. enrollment is 20.0 FTE 2. Less in CNR1, overall is ~75% |
| Student Leadership (Service Learning / Internships) | 1. 10 NR 2 Interns; 2. At least 5 additional internships 3. At least 1 new student stipend | 1. 10 students complete Internships 2. 5 complete other internships 3. 1 student gets new funding | 1. Dan 2. Dan 3. Dan | 1. 6/15 2. 6/15 3. 6/15 | 1. 12 NR2 interns 2.~10 options interns 3. Poss. thru NOSC |
| Staff (Hiring / Professional Development) | 1. Keep 1.0 PA Teacher + 0.4 cultural resources teacher; 2. 2 NR Options and 1 NR Science teacher for summer school | 1. NR teacher full-time all year, CR teacher 0.4 FTE all year 2. 3 NR teachers hired for summer | 1. Dan/Peggy 2. Dan/Peggy | 1. 6/15 2. 5/15 | 1. CR teacher removed 2. 1 teacher for summer |
| Safety / Risk Management | 1. Wilderness 1st Responder recert; 2. Document all incidents/near misses | 1. Full-time teacher obtains cert. 2. Incident forms posted in ‘Class Resources’ on CNR1 website | 1. Dan 2. Dan | 1. 2/15 2. 6/15 | 1. Cert. obtained 2. All incidents posted (3 total) |
| Other: | 1. Math credit equivalency petition completed 2. Enroll students for college credit through CWU and Pen. Col. | 1. Math credit equivalency granted for 2015-16 2. At least one student earns college credit with each college | 1. Dan 2. Dan | 1. 6/15 2. 6/15 | 1. Math credit petition denied 2. 1 student w/PC, 3 with CWU |

North Olympic Peninsula Skills Center

2013-2014 Work Plan Report

Program Name: Natural Resources								Date Submitted: September 2014

| Program Area | Indicator of Success | Outcomes | Individual(s) Responsible | Timeline | End of Year Review: |
| --- | --- | --- | --- | --- | --- |
| Curriculum / Instructional Materials | 1. Successfully go through CTE Program Re-approval 2. Social Studies credit for CNR1 3. Most cultural lessons on website | 1. Program is re-approved 2. CNR1 students get credit 3. Students access cultural lessons | 1. Dan/Ron 2. Dan/Jamie 3. Jamie | 1. 10/13 2. 10/13 3. 6/14 | 1. Ron submitted in June, no word back 2. SS credit awarded 3. Some lessons |
| Equipment / Facility | 1. Forks crew gets equipment necessary for SeaGrant Surveys 2. Get size 16-17 boots and waders | 1. Students from Forks use new survey equipment 2. All students properly outfitted | 1. Dan 2. Dan | 1. 1/14 2. 11/14 | 1. Purchased and used by students 2. Boots acquired |
| Student Recruitment / Retention | 1. 15.0 FTE total average; 2. Retain 60% of NR 1 students; | 1. Enrollment meets 15.0 FTE 2. 60% complete portfolios | 1. All/Dan/Ron 2. Dan/Ron/ Students | 1. 6/14 2. 6/14 | 1. 15.86 for school year+4.2 in summer- full-year program breaks even including 25% overhead (see budget docs. in advisory minutes) 2. >60% retained |
| Student Leadership (Service Learning / Internships) | 1. 5 NR 2 Interns starting in Jan; 2. At least 2 additional internships 3. At least 2 new scholarships | 1. 5 students complete Internships 2. 2 complete other internships 3. 2 students get scholarships | 1. Dan 2. Dan 3. Dan | 1. 1/14 2. 6/14 3. 6/14 | 1. 8 NR2 students 2. >2 other interns 3. Sea Grant + MRC |
| Staff (Hiring / Professional Development) | 1. Keep 1.0 PA Teacher + 0.4 cultural resources teacher; 2. NR Options and NR Science teachers teach summer school | 1. NR teacher full-time all year, CR teacher 0.4 FTE all year 2. 24 or more students earn credit through NR over summer | 1. Dan/Ron 2. Ron | 1. 6/14 2. 6/14 | 1. Full-staffing for year 2. 42 enrolled, >35 earn credit |
| Safety / Risk Management | 1. Plan for a student-friendly risk management manual; 2. Document all incidents/near misses | 1. Document is created showing vision + plan for manual 2. Incident forms posted in ‘Class Resources’ on CNR1 website | 1. Dan 2. Dan | 1. 6/14 2. 6/14 | 1. Conversations with Marie – no plan 2. All incidents posted on CNR1 site |
| Other: | 1. Enroll students for college credit through CWU | 1. At least one student earns college credit | 1. Dan | 1. 6/14 | 1. 1 student chose CWU credit |

North Olympic Peninsula Skills Center

2012-2013 Work Plan Report

Program Name: Natural Resources								Date Submitted: October 2013

| Program Area | Indicator of Success | Outcomes | Individual(s) Responsible | Timeline | End of Year Review: |
| --- | --- | --- | --- | --- | --- |
| Curriculum / Instructional Materials | 1. Successfully go through CTE Program Re-approval 2. English credit for NR 1 class | 1. Program is re-approved 2. NR 1 students get English credit | 1. Dan/Ron 2. Dan | 1. 6/13 2. 1/13 | 1. Dan submitted in Apr– Ron in Aug – awaiting approval 2.0.5 Eng. credits |
| Equipment / Facility | 1. Have Forks + Sequim NR SCP options available and accessible for students | 1. Students from both Forks and Sequim enroll and earn credit through NOPSC | 1. Dan | 1. 1/13 | 1. A handful from both locations enrolled and ½ earned credit |
| Student Recruitment / Retention | 1. 17.0 FTE total; 2. Students + NOPSC Director play role of recruiters; 3. Retain 75% of NR 1 students; 4. Website updated with marketing | 1. Enrollment meets 17.0 FTE 2. Students in classrooms, Director regularly meets with counselors 3. 75% complete portfolios 4. New website attracts | 1. All/Dan/Ron 2. Dan/Ron/ Students 3. Dan/Advisors 4. Dan/Ron | 1. 9/12 2. 3/13 3. 6/13 4. 1/13 | 1. Only 8-10 FTE 2. Students in all PAHS science, Director?? 3. Retained 20% 4. Dan did it in Aug |
| Student Leadership (Service Learning / Internships) | 1. 5 AmeriCorps starting in Jan; 2. At least 2 additional internships | 1. 5 students complete AmeriCorps 2. 2 students complete other internships | 1. Dan 2. Dan | 1. 1/13 2. 6/13 | 1. 3 before AC ended (2 were lined up) 2. 1 other full-time, 1 part-time |
| Staff (Hiring / Professional Development) | 1. Keep 1.0 PA Teacher, consider 0.25 cultural resources teacher; 2. Grant funding to pay for support for NR Options/SCP staff | 1. Teacher full-time all year, cultural resources teacher hired 2. Funding received and put toward support staff person | 1. Dan/Ron 2. Dan | 1. 6/13 2. 6/13 | 1. 0.4 cultural teacher hired 2. New summer NR Options with Tara Morrow hired |
| Safety / Risk Management | 1. WFR Recert for PA teacher; 2. Document all incidents/near misses | 1. WFR Recert completed 2. Incident report forms posted in ‘Class Resources’ on NR 1 website | 1. Dan 2. Dan | 1. 2/13 2. 6/13 | 1. Completed 2. All reports are posted |
| Other: | 1. Apply for 3-Year STEM funding and receive it; 2. Research possibility of community service college credit for students | 1. STEM funding used to help NOPSC Natural Resources 2. Find out if articulation is possible for 2013-2014 school year | 1. Dan 2. Dan | 1. 1/13 2. 6/13 | 1. STEM funding not available, MRC yes 2. 2 credits per semester with CWU |

North Olympic Peninsula Skills Center

2011-2012 Work Plan Report

Program Name: Natural Resources								Date Submitted: September 2012

| Program Area | Indicator of Success | Outcomes | Individual(s) Responsible | Timeline | End of Year Review: |
| --- | --- | --- | --- | --- | --- |
| Curriculum / Instructional Materials | 1. Assignments in print and on Moodle in student-friendly format 2. Workbook for 4-H Stewardship 3. NR QUEST Skills Manual | 1. Students access and learn from printed materials and Moodle site 2. PT and Chimacum use book 3. Skills Manual used by students | 1. Dan 2. Dan 3. Dan | 1. 6/12 2. 9/11 3. 2/11 | 1. Success 2. PT yes, Chimacum no 3. Success |
| Equipment / Facility | 1.Identify permanent Forks + Sequim classrooms if classes are a go 2. Purchase Sequim equipment | 1. Classroom(s) identified for 2011-2012 school year 2. Complete purchases | 1. Forks: ??____ Sequim: ??_____ 2. Dan + Sequim | 1. 6/11 2. 6/11 | 1. No classes offered 2. Success with NFWF Grant |
| Student Recruitment / Retention | 1. 17.0 FTE total; 2. Students + NOPSC Assistant Director play role of recruiters; 3. Website updated and linked; 4. Retain 75% of NR 1 students | 1. Enrollment meets 17.0 FTE 2. Students and Advisory Board Members go into classrooms 3. New website uploaded 4. 75% complete portfolios | 1. All/Cindy 2. Dan/Renee 3. Dan/Renee 4. Dan/Cindy | 1. 9/11 2. 3/12 3. 9/12 4. Ongoing | 1. first semester yes, second no 2. Students yes, advisors no 3. no 4. 50% or less retention |
| Student Leadership (Service Learning / Internships) | 1. Continue ongoing projects; 2. Bring on 1 more project for PA; 3. Student as Newsletter Editor | 1. Current projects continue 2. New project identified 3. At least three newsletters done | 1. Dan 2. Dan 3. Dan | 1. Ongoing 2. 6/12 3. 6/12 | 1. Success 2. Compost 3. 4 Newsletters |
| Staff (Hiring / Professional Development) | 1. Find funding to support 2 Huxley interns; 2. Hire Sequim Teacher | 1. Interns are compensated for their service 2. Hire Sequim Teacher | 1. Dan/Cindy 2. Cindy | 1. 8/12 2. 8/10 | 1. no funding – interns volunteered 2. no class |
| Safety / Risk Management | 1. WFR for Sequim teacher; 2. Document all incidents/near misses | 1. WFR Cert completed 2. Incident report forms posted in ‘Class Resources’ on NR 1 website | 1. Sequim 2. Dan | 1. 8/12 2. 6/12 | 1. no class in Sequim 2. Success |
| Other: | 1. Get students through GIS Tech Prep articulation; 2. Explore 2nd Tech Prep to replace the one that went away in 6/11; 3. Use Work Plan as Program Evaluation Tool | 1. Students complete Tech Prep for GIS 2. Able to decide if additional articulation is possible for 2011-12 3. Acceptable or exemplary results | 1. Dan 2. Dan 3. Roy+Nancy | 1. 11/11 2. 1/12 3. 6/12 | 1. no students selected this 2. Green River CC is possible, but not desired 3. Success – suggest using 4 pt. scale |

North Olympic Peninsula Skills Center

2010-2011 Work Plan Report

Program Name: Natural Resources								Date Submitted: October 2011

| Program Area | Indicator of Success | Outcomes | Individual(s) Responsible | Timeline | End of Year Review: |
| --- | --- | --- | --- | --- | --- |
| Curriculum / Instructional Materials | 1. New Salmon/Fisheries Unit including guest speaker(s); 2. ‘Connections’ Curriculum for Senior Culminating Projects; 3. Assignments on Moodle in student-friendly format 4. New CTE Framework Alignment | 1. NR 1 Students complete unit with guest speaker(s) 2. Students progress through SCP + Curriculum approved by PAHS 3. Students access and learn from Moodle site 4. Framework accepted by state | 1. Dan/Kim 2. Dan/Cindy 3. Dan 4. Dan | 1. 10/10 2. 5/11 3. Ongoing 4. 9/10 | 1. Success 2. Success 3. Success, format could be improved 4. Success |
| Equipment / Facility | 1. Inventory gear + new purchases; 2. Identify permanent Forks + Sequim classrooms | 1. Inventory completed, purchases 2. Classroom(s) identified for 2011-2012 school year | 1. Dan 2. Forks: ??____ Sequim: ??_____ | 1. 6/11 2. 6/11 | 1. Inventory done 2. No – Low Sequim enrollment, Forks building not done |
| Student Recruitment / Equity | 1. 20 students total; 2. Students + Advisory Board play role of recruiters; 3. Website updated and linked; 4. Accept all students | 1. Enrollment 20 total 2. Students and Advisory Board Members go into classrooms 3. New website uploaded 4. No students declined enrollment | 1. All/Cindy 2. Dan/ ??_____ 3. Dan 4. Dan/Cindy | 1. 9/10 2. 3/11 3. 9/10 4. Ongoing | 1. Exceeded 2. Students yes, Advisors no 3. Success 4. Success |
| Student Leadership (Service Learning / Internships) | 1. Continue ongoing projects; 2. Bring on 1-2 more projects for Sequim (and possibly PA); 3. Pilot internships with NPS | 1. Current projects continue 2. New project(s) identified 3. At least three student interns | 1. Dan 2. Dan/??______ 3. Dean/??_____ | 1. Ongoing 2. 6/11 3. 6/11 | 1. Success 2. Identified, not used 3. One ONP intern |
| Staff (Hiring / Professional Development) | 1. Teacher plus support staff (Para or Americorps/College Intern) for each location with 10+ students; 2. WBL Cert for PA teacher | 1. Staff hired and trained 2. Staff member through with WBL certification class | 1. Dan/Cindy 2. Dan | 1. 8/10 2. 8/10 | 1. Only 1 teacher 2. Success |
| Safety / Risk Management | 1. WFR Re-cert for teacher; 2. Review + Update Risk Management Plan | 1. WFR Re-Cert completed 2. Plan approved by PASD and shared with other school districts | 1. Dan 2. Dan/??______ | 1. 2/11 2. 9/11 | 1. Success 2. Not reviewed by PASD – who should review? |
| Other: | 1. 1 Tech Prep articulation in-place at start of year; 2. Explore 2nd Tech Prep + Service learning credit 3. Use New Program Evaluation Tool | 1. Students enroll in Tech Prep 2. Able to decide if additional articulation is possible for 2011-12 3. Acceptable or exemplary results | 1. Dan 2. Dan 3. Roy+Nancy | 1. 11/10 2. 1/11 3. 6/11 | 1. Success, though students only did 1 2. 2nd Tech Prep for 1 student 3. Still in draft form |

North Olympic Peninsula Skills Center

2009-2010 Work Plan Report

Program Name: Natural Resources								Date Submitted: April, 2009

| Program Area | Indicator of Success | Outcomes | Individual(s) Responsible | Timeline |
| --- | --- | --- | --- | --- |
| Curriculum / Instruct. Materials | On-line resources True; Accepted/approved curriculum Not Reviewed | Students access and learn from Moodle site True; 2008-2009 curriculum used + improved True | Dan Lieberman; Janet Kearsley (support), Darek Staab/OPI (support) | 2009-2010 |
| Equipment / Facility | Functional toolkits True; Room 206 and Forks classroom outfitted (see ‘Current Needs Jul + Dec) True | Toolkits get used True; Students + teachers have what they need to run class Ususally | Dan Lieberman; Jake Jackson | 2009-2010 |
| Student Recruitment / Equity | High School counselors, science teachers, principals and students are aware of class offering Progress – Teacher + Students Presented in 20 PA classes, 3 Community events, | Enrollment (8-10 from PA/Sequim) True – All from PA; Articles: 2 PDN, 1 Forks Forum, 2 PASD, 1 Streamkeepers Newsletter | Students are knowledgeable about and self-select into the class; Dan Lieberman; Liam Antrim (PA/Sequim support) | 2009-2010 |
| Student Leadership (Service Learning / Internships) | New project(s) defined One; Continue with Hoh project, on Hoh project: to have classes regularly using field sites and learning to recognize species, landforms, hydrology, ecological processes, as well as to use equipment Not True; Pilot internships for 2nd yr students True | Initiation of new project(s) True; Hoh – to be able to produce an accurate map using a computer, to assemble baseline info into a site description and knowledge of ecological processes to produce a professional level application for a salmon habitat recovery project. Not True | Dan Lieberman; Mike Hagen (West End support); Jack Ganzhorn (class framework and internship planning support) | 2009-2010 |
| Staff (Hiring / Professional Development) | Each classroom/class location has professional staff + one more person than locations No; staff members en-route to needed certifications True | Staff hired and trained Mostly True; staff members enrolled in or through with certification programs Enrolled in | Dan Lieberman; Janet Kearsley (hiring support); Roy and Nancy (certification + professional development support) | 2009-2010 |
| Safety / Risk Management | Risk Management plan reviewed Not Reviewed by PASD; Professional staff enrolled in WFR certification True for Teacher, not PA Para | Risk Management plan approved by PASD and shared with other member school districts Not Officially; WFR Certification for all professional staff Not True | Dan Lieberman; Jeff Ward (document review support) | 2009-2010 |
| Other: | Class schedule/format allows realization of vision True; Marketing materials updated True; Needs assessment conducted + usable opnrc; COMPASS test Not True | 2.5 hour block class True; Marketing video on internet + distributed Not True; teacher + students regularly access resource database Somewhat True | Dan Lieberman; Clea Rome (grant writing); | 2009-2010 |

North Olympic Peninsula Skills Center

Report from 2008-2009

Program Name: Natural Resources								Date Submitted: March 3, 2009

| Program Area | Report from 2008-2009 (People who played large and/or key support roles in making specific items happen are in parentheses) |
| --- | --- |
| Curriculum / Instructional Materials | Beetles (Darek), Streamkeepers, Mapping (Dwight), Habitat Assessment, Forest Eco/Timber Mgmt, Geology, Wetlands (Darek), units developed. Materials: Internet, news, Field guides/manuals, Project WET (Janet). Needs: iTV-friendly curriculum, teacher-free activities, service learning projects + supporting curriculum. |
| Equipment / Facility | Purchased: iTV setup (Jake), computers (SKC IT-tech), field guides, binoculars, 1st Aid kit, All needed field equipment was borrowed from partners. Facility: Rm. 206 partially outfitted (Jake), Forks room set up (Adria) Needs: Basic flexible field supplies (measuring tapes, magnifiers, collection tools, etc), Room 206 finished |
| Student Recruitment / Equity | Large enrollment from Forks (Rupprecht), 1 from Port Angeles, 0 from elsewhere. 2 Forks POSSE students dropped due to iTV, 4 of 7 ELL and 1 of 3 Native students remain. Now, mtgs. w/counselors, admin, + science Needs: Students from the Eastern Peninsula, extra support for students with extra needs. |
| Student Leadership (Service Learning / Internships) | True service learning with Streamkeepers and Wetlands Birds (Darek). Moderate service learning with Beetle Blitz (Darek). Hoh River Trust Grant Project for 09-10 (Mike). Initial internship conversations with partners. Needs: Service Learning Projects for future years, Internship opportunities for school-year + summer. |
| Staff (Hiring / Professional Development) | Dan hired 7/08 (Jake). Adria Williams hired 10/08. Dan’s 08-09 PD plan written, Roy and Nancy recruited to consult about PD, class observation, Dan presented at WALA conference and will update WFR certification. Needs: WFR Cert. for Para, Teaching Cert. for Teacher, Ways to reach vision with 2-3 class locations. |
| Safety / Risk Management | Field Risk Management Manual Draft submitted to PASD 9/08. In-class incident reporting system developed. Attempted to contact NPS to use park radio safety net. Needs: Risk Management Manual update + review, NPS partnership for radio safety net, WFR training. |
| Other: | Many partnerships have been established, particularly on West End (Mike). Underway is research into feasibility of and funding for a natural resources opportunities/needs survey (Clea). 500 dollars to commission a promotional video was approved by NOPSC. Tech Prep credit has not been arranged despite many inquiries to the coordinator for this. Dan estimates ~40 hours per week for Natural Resources, a 0.5 FTE job. Needs: Partnerships focused on service learning, Opportunities/Needs survey, Marketing strategy and materials, Tech Prep credit for students with any college, increased support for teacher. |